## Capacity Planning
Capacity Planning
Project |  |  | Project Manager
[Project Name] |  |  | [Name of project manager]
Department | Start Date |  | End Date
[Add department] | [Start date] |  | [End date]
Task | Duration (Hours) |  | Start Date | End Date
[Task name & description] | [How long the task is in hours] |  | [Start date] | [End date]
Resource | Hourly Rate | Resource Availability (hours per month) | Week 1 | Week 2 | Week 3 | Week 4 | Resource Utilization (hours per month) | Remaining Resource Availability (hours per month) | Resource Utilization Rate | Cost
Brad | 30 | 160 | 10 | 10 | 10 | 10 | 40 | 120 | 25% | 1200
Nicole | 40 | 160 | 30 | 20 | 20 | 20 | 90 | 70 | 56.25% | 3600
Jane | 50 | 160 | 40 | 40 | 40 | 20 | 140 | 20 | 87.5% | 7000
Bob | 50 | 160 | 40 | 40 | 40 | 20 | 140 | 20 | 87.5% | 7000
Michael | 30 | 80 | 20 | 40 | 0 | 20 | 80 | 0 | 100% | 2400
Ashley | 45 | 160 | 0 | 0 | 40 | 40 | 80 | 80 | 50% | 3600
Mark | 60 | 80 | 15 | 15 | 15 | 15 | 60 | 20 | 75% | 3600
Free Related Templates
Project Budget Template
Gantt Chart Template
Resource Plan Template
Project Plan Template
Project Dashboard Template